## Slide 1
Presentation title
Confidential – For client internal use only
Prepared by: [Consulting Firm Name]
[Today’s Date]

## Slide 2
Executive Summary & Recommendation
AI adoption is now a strategic imperative: 90% of Fortune 500 companies plan to increase AI budgets by 2026. Early adopters report 25–40% cost savings and 2–3x faster decision-making.
We recommend a phased AI adoption, starting with a 90-day pilot, to unlock $15M in efficiency gains and a 3.5x ROI over three years. Immediate action will secure competitive advantage and future-proof your organization.

## Slide 3
Client Context & Objectives
Current Context & Objectives
Current context: Increasing market competition, rising operational costs, and demand for faster, data-driven decisions.
Key constraints: Upfront investment ($2M+), data security, and workforce readiness.
Objectives: Achieve 12% revenue uplift in year one, reduce costs by 25–40%, and accelerate decision-making by 2–3x.
In scope: Customer support, sales forecasting, and operational automation.
Out of scope: Non-core business units in phase one.. Describe the image on the left or provide insight into the subject. Use multiple sentences to occupy the space and demonstrate alignment.

## Slide 4
Proposed Approach & Methodology
1
Step 1
90-day pilot: Identify high-impact use cases, rapid prototyping, and stakeholder workshops. Use succinct language to guide your audience.
2
Step 2
6-month scale-up: Expand to additional functions, integrate with existing systems, and conduct training. Use succinct language to guide your audience.
3
Step 3
Year 2 enterprise rollout: Full deployment, change management, and benefits tracking. Use succinct language to guide your audience.
4
Step 4
Methods: Data analysis, process mapping, AI tool selection, and collaborative sprints with client teams. Use succinct language to guide your audience.

## Slide 5
Workplan, Timeline & Milestones
1
Step 1
Week 1–4: Use case selection, data readiness assessment Use succinct language to guide your audience.
2
Step 2
Week 5–12: Pilot implementation, initial results review Use succinct language to guide your audience.
3
Step 3
Month 4–9: Scale-up to core functions, user training Use succinct language to guide your audience.
4
Step 4
Month 10–24: Enterprise rollout, continuous improvement Use succinct language to guide your audience.

## Slide 6
Deliverables & Success Metrics
1
Key Deliverables
AI pilot report, implementation roadmap, training materials, and benefits realization dashboard. goes here. Explain the key point succinctly.
2
Success Metrics
Success Metrics content goes here. Provide additional details or context.
3
Tracking & Review
Benefits tracked via quarterly KPI reviews and post-implementation surveys. for section 3 content. Elaborate on the subject matter.

## Slide 7
Team, Roles & Ways of Working
1
Consulting Team
AI strategy lead, data scientist, change manager, project manager. goes here. Explain the key point succinctly.
2
Client Team
Client Team content goes here. Provide additional details or context.
3
Ways of Working
RACI: Consultants drive analysis and implementation; client leads provide data and champion adoption. Weekly check-ins, Slack/Teams for daily comms, 24-hour response SLA, shared project workspace. for section 3 content. Elaborate on the subject matter.

## Slide 8
Relevant Experience & Case Studies
1
Case 1: Customer Support Automation
Fortune 500 client automated customer support, reducing ticket handling time by 40% and saving $4M/year. goes here. Explain the key point succinctly.
2
Case 2: AI Sales Forecasting
Case 2: AI Sales Forecasting content goes here. Provide additional details or context.
3
Additional Notes
Testimonials available upon request. All cases delivered with robust data security and workforce transition plans. for section 3 content. Elaborate on the subject matter.

## Slide 9
Commercials, Assumptions & Terms
1
Pricing
$2M+ upfront investment for pilot and scale-up, with flexible payment milestones. goes here. Explain the key point succinctly.
2
Assumptions
Assumptions content goes here. Provide additional details or context.
3
Terms
Standard consulting agreement, monthly invoicing, change control for scope adjustments. for section 3 content. Elaborate on the subject matter.

## Slide 10
Risks, Mitigations & Next Steps
1
Top Risks
Data security, workforce transition, change resistance, ROI realization. goes here. Explain the key point succinctly.
2
Mitigations
Mitigations content goes here. Provide additional details or context.
3
Next Steps
Confirm sponsorship, schedule kickoff, provide data access, and align key stakeholders for pilot launch. for section 3 content. Elaborate on the subject matter.